## Test Case Plan
SCRUM-28 Test Coverage Plan
GREEN on 14 Oct 2026: 3 isolated backend Unit tests and 15 draft-page cases passed. Focused rechecks passed after two additive assertions. Five backend extensions and stale-state Integration remain unverified. Execution status is column O.
Test Case ID | Acceptance Criterion (AC1-AC6) | Test Scenario / Description | Test Type (Unit / Frontend Unit / Integration) | Preconditions | Test Steps / Input | Expected Result | Coverage Status (Covered / Partial / Missing) | Action (Reuse Existing / Extend Existing / Add New) | Existing Test File and Method | Actual New / Extended Test File and Method | Priority (Essential / Optional) | Remarks / Dependencies | Real Database Required? | Execution Status | Result / Reason | Execution Command / Evidence
TC-28-01 | AC1 | All ten request fields survive saving and reopening. | Integration | DR-SEED complete draft D2; authenticated owner. | Open D2 and compare every DRAFT_FIELDS value with COMPLETE. | All saved values return, including accessibility, equipment, registration and Singapore-local start/end. | Partial | Reuse Existing | backend/tests/test_event_drafts.py ReopenTests.test_reopening_shows_everything_previously_saved | No new or extended method | Essential | Actual assertions inspected. AC1 persistence covered; UI entry is TC-28-02. Backend reuse not executed in RED. | Yes | Not run | Existing backend round-trip retained; not executed in RED. No runtime pass claimed. Remains unexecuted in GREEN; no DB retry. | No DB reuse run.
TC-28-02 | AC1, AC4; supports AC3 | Enter all ten fields; show confirmation and the existing event ID. | Frontend Unit | DraftEventPage and mocked API; complete edited form with optional details. | Extend existing success case: fill all ten inputs; assert save body. Hold save pending and check busy inputs; resolve save then submit. | Current values sent; busy form cannot lose edits; visible confirmation contains Request #7; Submitted form is read-only. | Covered | Extend Existing | frontend/src/pages/DraftEventPage.test.jsx it("saves the current edits, then submits, and shows the request as Submitted") | frontend/src/pages/DraftEventPage.test.jsx it("saves the current edits, then submits, and shows the request as Submitted") | Essential | P1/P5 implemented. Original success assertions preserved; no parallel form or new page. | No | Pass | All-field save body, visible Request #7, confirmation, submitted read-only inputs and pending-input protection passed. | npm.cmd test -- src/pages/DraftEventPage.test.jsx --reporter=json --outputFile=C:/Users/Mikhail/AppData/Local/Temp/scrum28-frontend-green.json
TC-28-03 | AC2, AC3 | Reuse validation; add existing-rule boundaries and protected-field probes. | Integration | Owner and draft D1; AppTestCase transaction. | Reuse invalid kinds/unknown field/malformed JSON. Extend with 255/256-character title and forged organiser_id/coordinator_id/status. | Invalid values return 400 naming field; saved values unchanged. Title 255 accepted; 256 refused. Ownership/status cannot be forged. | Partial | Extend Existing | backend/tests/test_event_drafts.py SaveIncompleteTests.test_values_of_the_wrong_kind_are_refused backend/tests/test_event_drafts.py SaveIncompleteTests.test_an_event_name_is_required | backend/tests/test_event_drafts.py SaveIncompleteTests.test_values_of_the_wrong_kind_are_refused | Essential | Only coverage additions: production parser already enforces these rules. No new validation policy. | Yes | Not run | Additive title boundaries/protected fields written; real-DB extension not executed. Remains unexecuted in GREEN; no DB retry. | Deferred DB execution after the single blocked integration attempt.
TC-28-04 | AC2, AC3; supports AC4 | Missing data/time errors block submission; incomplete drafts remain saveable. | Integration | DR-SEED incomplete D1 and complete D2; owner. | Reuse incomplete submission, optional-field, save-never-submits and end equal/before/after start cases. | Missing labels/corrections returned; refused request unchanged. Optional fields may be null. Bad ordering can be saved as Draft, but not submitted. | Partial | Reuse Existing | backend/tests/test_event_drafts.py SubmissionTests.test_an_incomplete_draft_cannot_be_submitted backend/tests/test_event_drafts.py SubmissionTests.test_optional_fields_are_not_needed_to_submit backend/tests/test_event_drafts.py SubmissionTests.test_end_must_be_after_start_to_submit backend/tests/test_event_drafts.py SubmissionTests.test_saving_never_submits | No new or extended method | Essential | Reuse SCRUM-29 A7/A9: eight required fields, end > start, naive Singapore times. Retain SCRUM-29 validation working assumptions. | Yes | Not run | Existing required/optional/time-order/draft tests reused without edits; not executed. Remains unexecuted in GREEN; no DB retry. | No DB reuse run.
TC-28-05 | AC3; supports AC6 | Missing-field refusal explains corrections and retains edits. | Frontend Unit | Draft loaded; save succeeds; submit returns missing list. | Edit Purpose, click Submit for review; inspect alert and controls. | Missing field labels shown; entered purpose retained; Draft remains editable. | Covered | Reuse Existing | frontend/src/pages/DraftEventPage.test.jsx it("lists the missing fields when submission is refused, and stays a Draft with the edits kept") | No new or extended method | Essential | Current assertions satisfy scenario. Invalid end-time recovery is TC-28-13. Inline highlighting not required. | No | Pass | Existing missing-field messages and retained current values passed with status reconciliation. | npm.cmd test -- src/pages/DraftEventPage.test.jsx --reporter=json --outputFile=C:/Users/Mikhail/AppData/Local/Temp/scrum28-frontend-green.json
TC-28-06 | AC2-AC6 (security) | Authentication and missing-record failures protect submission. | Integration | Existing session and missing-ID fixtures. | Reuse submission without token, expired/deleted-user token, and unknown event ID. | 401 for invalid session, 404 for missing request; no draft mutation. | Partial | Reuse Existing | backend/tests/test_event_drafts.py SaveIncompleteTests.test_a_valid_session_is_required backend/tests/test_event_drafts.py ReopenTests.test_unknown_draft_returns_not_found | No new or extended method | Essential | No JWT redesign. Other malformed-token handling remains SCRUM-27 regression scope. | Yes | Not run | Existing session/missing-record tests reused; not executed. Remains unexecuted in GREEN; no DB retry. | No DB reuse run.
TC-28-07 | AC2-AC6 (security) | Only the current organiser owner can submit. | Integration | Own/other drafts; owner token issued while role organiser. | Reuse other-organiser/coordinator denials. Extend submit probes to admin/attendee/venue/tech roles and owner role changed using same token. | 403 without private details or mutations. Stored organiser role plus ownership required. | Partial | Extend Existing | backend/tests/test_event_drafts.py ReopenTests.test_another_users_draft_cannot_be_opened_saved_or_submitted | backend/tests/test_event_drafts.py ReopenTests.test_another_users_draft_cannot_be_opened_saved_or_submitted | Essential | Current checks already implement the rule. Extend relevant coverage; preserve SCRUM-27 permissions. | Yes | Not run | Additional roles/old-owner-token probes written; not executed. Remains unexecuted in GREEN; no DB retry. | Deferred DB execution.
TC-28-08 | AC4; supports AC5 | Submit the same request row with all details intact. | Integration | Complete D2; owner; agreed assignment fixture. | Record owner count and ID; submit; compare returned/stored fields and draft list. | 200; same ID/count; submitted status/time stored; details unchanged; removed from draft list. | Partial | Extend Existing | backend/tests/test_event_drafts.py SubmissionTests.test_submitting_a_complete_draft | backend/tests/test_event_drafts.py SubmissionTests.test_submitting_a_complete_draft | Essential | Existing test covers status/time/details, but lacks explicit response-ID/count checks. Handoff is TC-28-09. No model fields required. | Yes | Not run | Same-ID/count assertions added; DB extension not executed. Remains unexecuted in GREEN; no DB retry. | Deferred DB execution.
TC-28-09 | AC4; supports AC5 | Automatic assignment gives the new submission to its authorised reviewer. | Unit | Isolated Flask/JWT app; unordered fixture users, eligible IDs 9 and 5; smaller IDs have non-coordinator current roles. | Submit route; retrieve coordinator/managed list/review. Review as selected coordinator, other coordinator and organiser. | Same Submitted ID and assignment/time saved atomically. Selected coordinator lists/reviews all details; others get 403. No venue booking/resource reservation created. | Covered | Add New | backend/tests/test_event_decisions.py WhoAndWhenTests.test_coordinator_opens_the_full_request_to_review_it [downstream only] | backend/tests/test_event_submission.py SubmissionUnitTests.test_submission_assigns_reviewer_and_preserves_access_boundaries | Essential | P2 implemented: current coordinator role, lowest ID; no candidate -> retryable 503 before mutation. Reviewer scope/manual reassignment unchanged. Unit results do not prove PostgreSQL ordering/persistence. | No | Pass | Lowest current coordinator ID selected over unordered fixtures; same ID/details and single commit; authorised reviewer access and other-role denials passed. Unit fake, not DB transaction/query execution proof. | .\.venv\Scripts\python.exe -B -m unittest -v tests.test_event_submission.SubmissionUnitTests
TC-28-10 | AC4, AC6 | No eligible coordinator follows the agreed failure/outcome policy. | Unit | Complete owned Draft; in-memory query has no current coordinator-role users. | Submit; assert approved no-candidate response/state and preserved information. | HTTP 503 with retryable=true and clear no-coordinator explanation. Draft/details/status/submission and assignment timestamps unchanged; no commit/add. Later eligible-role change permits same-ID retry. | Covered | Add New | None for this scenario | backend/tests/test_event_submission.py SubmissionUnitTests.test_no_eligible_coordinator_uses_agreed_submission_outcome | Essential | Approved no-candidate policy implemented and Unit-tested, including retained Draft/details and same-ID retry. | No | Pass | No current coordinator: 503/retryable, unchanged Draft/details/audits and no commit/add; later same-ID retry passed. Database-independent. | .\.venv\Scripts\python.exe -B -m unittest -v tests.test_event_submission.SubmissionUnitTests
TC-28-11 | AC5; supports AC4 | Repeated submission stays one event; separate identical requests allowed. | Integration | Owner complete draft and submitted fixture; approved assignment fixtures. | Keep GET/PUT/submit non-draft refusals. Add submit D2 then repeat; compare count/ID/time/coordinator. Create two identical complete drafts and submit their different IDs. | Repeat returns existing 409; original row/count/time/assignment unchanged. Distinct IDs with identical details can both submit. | Partial | Extend Existing | backend/tests/test_event_drafts.py ReopenTests.test_submitted_request_cannot_be_reopened_as_a_draft | backend/tests/test_event_drafts.py ReopenTests.test_submitted_request_cannot_be_reopened_as_a_draft | Essential | Current test starts with seeded S1; extend real transition/count assertions. Known ID suffices for duplicate row prevention. Unknown first-create response is D2, not solved by this case. | Yes | Not run | Real-transition repeat/row-count and separate identical-request assertions added; not executed. Remains unexecuted in GREEN; no DB retry. | Deferred DB execution.
TC-28-12 | AC6; supports AC4 | Confirmed commit failure rolls back submission and allows same-ID retry. | Integration | Complete draft; agreed assignment fixture; commit fails before success. | Extend existing failure with full snapshot; compare after failure; retry same ID after recovery. | 503 with reason/retryable; Draft details/audit/assignment unchanged; recovery submits same ID without partial assignment. | Partial | Extend Existing | backend/tests/test_event_drafts.py SaveFailureTests.test_failed_submission_leaves_the_draft_as_a_draft | backend/tests/test_event_drafts.py SaveFailureTests.test_failed_submission_leaves_the_draft_as_a_draft | Essential | Current assertions only Draft/no submitted_at. Add whole-transaction and retry checks. P2; keep confirmed rollback semantics. | Yes | Not run | Full snapshot and same-ID retry added; rollback durability remains unverified in RED. Remains unexecuted in GREEN; no DB retry. | Deferred DB execution; do not infer transaction guarantees from mocks.
TC-28-13 | AC3, AC6 | Submit-stage rejection retains values and supports retry. | Frontend Unit | Current complete form; save PUT succeeds; submit returns end_time 400 or confirmed pre-commit 503. | One parameterised it(): submit; assert explanation/all values; retry after correction or recovery. | Useful correction/failure shown; values retained; controls recover; same ID saves/submits on retry. | Covered | Add New | frontend/src/pages/DraftEventPage.test.jsx it("keeps the edits and the last-saved time when saving fails (%s), and saves on retry") [save-stage only] | frontend/src/pages/DraftEventPage.test.jsx it.each("retains request details after submit rejection and retries the same request (%s)") | Essential | Observed: both submit-stage failure variants pass existing production. Coverage added without forcing a production change. | No | Pass | Both submit-stage variants passed: end-time 400 and pre-commit 503 retain all current values and retry same ID. | npm.cmd test -- src/pages/DraftEventPage.test.jsx --reporter=json --outputFile=C:/Users/Mikhail/AppData/Local/Temp/scrum28-frontend-green.json
TC-28-14 | AC5, AC6; supports AC4 | Reconcile lost submission response using known ID. | Frontend Unit | Save returned ID 7; submit response lost; owner requests/mine and draft GET mocked. | One parameterised it(): uncertain POST, then status check/retry. Exercise non-draft receipt, positively confirmed Draft, and unavailable reconciliation. | Known non-draft shows receipt/current status/reference and blocks edit. Confirmed Draft retries only ID 7. Unavailable check keeps inputs and uncertainty explanation. Never create another event or infer Draft just from missing list entry. | Covered | Add New | frontend/src/pages/DraftEventPage.test.jsx it("saves the current edits, then submits, and shows the request as Submitted") [normal success only] | frontend/src/pages/DraftEventPage.test.jsx it.each("reconciles uncertain submission outcomes without creating another request (%s)") | Essential | P3 implemented using owner-scoped draft GET, then organiser mine list after 409. Check-status action cannot resubmit until Draft is established. Newer unsaved edits preserved. Creation-idempotency edge deferred to SCRUM-29. | No | Pass | Submitted/Draft/unavailable outcomes passed. Later receipt check preserves newer unsaved description edits; unknown outcomes make no extra submission. All API responses mocked. | npm.cmd test -- src/pages/DraftEventPage.test.jsx --reporter=json --outputFile=C:/Users/Mikhail/AppData/Local/Temp/scrum28-frontend-green.json After additive newer-edit assertion: npm.cmd test -- src/pages/DraftEventPage.test.jsx --testNamePattern 'reconciles uncertain submission' --reporter=json --outputFile=C:/Users/Mikhail/AppData/Local/Temp/scrum28-reconciliation-green.json
TC-28-15 | AC6; supports AC4 | Durable submission survives unavailable post-commit ORM reads. | Unit | Isolated Flask/JWT app; mocked successful commit; record injects SQLAlchemyError on subsequent column reads. | Invoke public submit route; mocked commit disables later field reads. Assert successful primitive response with ID/status/time and no rollback. No database durability claim. | Success response contains saved ID/status/time without post-commit reads; no false 'still a draft' 503. | Covered | Add New | backend/tests/test_decision_accountability.py SaveFailureTests.test_a_saved_decision_is_never_reported_as_failed [pattern; decision only] | backend/tests/test_event_submission.py SubmissionUnitTests.test_successful_submission_survives_post_commit_read_outage | Essential | P4 implemented: snapshot primitives before commit; flush creation to obtain ID. Invalidated COMMIT connection reports uncertainty. Existing Unit definition strengthened without removing assertions. | No | Pass | Response-read fault after commit returns primitive saved-success payload. Additional lost-COMMIT-acknowledgement subcase returns honest 503/outcome_uncertain and calls rollback. Fault injection, not DB durability proof. | .\.venv\Scripts\python.exe -B -m unittest -v tests.test_event_submission.SubmissionUnitTests After additive uncertain-commit subcase: .\.venv\Scripts\python.exe -B -m unittest -v tests.test_event_submission.SubmissionUnitTests.test_successful_submission_survives_post_commit_read_outage
TC-28-16 | AC4, AC5; supports AC3 | Stale draft writer cannot overwrite an already submitted request. | Integration | Complete draft cached; simulate another request's transition inside rolled-back fixture transaction. | Update underlying row to Submitted with original time/assignment without refreshing cached ORM object; attempt draft PUT and submit public routes. | 409; original details/time/assignment/count unchanged; no second event. | Partial | Add New | backend/tests/test_decision_accountability.py WhoAndWhenTests.test_a_decision_made_meanwhile_is_not_overwritten [pattern; decision only] | backend/tests/test_event_submission.py SubmissionPersistenceTests.test_stale_draft_cannot_overwrite_submitted_request | Essential | P6 implemented locally with with_for_update/populate_existing for draft writers. Real stale-state Integration test preserved and blocked; no database guarantees claimed. | Yes | Blocked | Implemented fresh row locking/identity-map refresh for both draft save and submit. Integration remains pending: RED sandbox denied connection before fixtures/assertions; no GREEN attempt. True persistence/concurrency guarantees unverified. | Not rerun in GREEN. Original restricted-DB attempt and setup error retained in execution history.
TC-28-17 | AC3, AC6 | Failed prerequisite save keeps input and prevents submission. | Frontend Unit | Draft loaded; save current edits returns 400/503/network failure. | Reuse retention/retry and no-submit-after-save-failure tests. | Useful explanation; edits/last saved time retained; failed save sends no submit POST; recovery saves same draft. | Covered | Reuse Existing | frontend/src/pages/DraftEventPage.test.jsx it("keeps the edits and the last-saved time when saving fails (%s), and saves on retry") frontend/src/pages/DraftEventPage.test.jsx it("does not submit when saving the edits first fails") | No new or extended method | Essential | Actual assertions inspected. TC-28-13 separately covers submit-stage failures; no duplicate test. | No | Pass | Existing save-stage 400/503/network retention/retry and no-submit-after-save-failure cases passed. | npm.cmd test -- src/pages/DraftEventPage.test.jsx --reporter=json --outputFile=C:/Users/Mikhail/AppData/Local/Temp/scrum28-frontend-green.json

## AC Coverage Summary
SCRUM-28 Acceptance Criterion Coverage
GREEN implemented; 18 distinct targeted cases passed (3 backend Unit, 15 Frontend Unit). No GREEN DB test ran. Stale-state Integration and five backend extensions remain pending. Full regression verification not performed.
Acceptance Criterion | Requirement Summary | Existing Coverage | Missing Coverage | Proposed New Tests | Implementation Required? (Yes / No / Pending Decision) | Dependencies / Decisions | Overall Status (Covered / Partially Covered / Not Covered / Blocked)
AC1 | Enter all ten request details. | All ten fields, saved body and current form values verified in the passing frontend success extension. Existing reopening passed. | Backend all-field round-trip reuse remains unexecuted; entry/UI behaviour is tested. | None. Extend TC-28-02; reuse TC-28-01. | No | Free text/yes-no and Singapore-local dates already implemented. | Covered
AC2 | Check existing required-field/validation rules. | Existing required-field/type/format rules retained. Complete-request Unit path and frontend missing/end-time correction cases passed. | Existing real-DB validation tests and title/protected-field/current-role extensions unexecuted. | None. Extend TC-28-03/07. | No | No new validation rules. Existing SCRUM-29 incomplete-draft and check-order contracts preserved by static review. | Partially Covered
AC3 | Prevent invalid submission; identify corrections; retain inputs. | Missing-field and submit-stage correction messages, retained inputs, busy-input protection and later reconciliation retention passed. | Real-DB invalid-save/state persistence assertions pending. | TC-28-13/16 shared; extend TC-28-02. | No | Inputs disabled only during pending operations/non-draft state. Reconciliation never replaces form values. | Covered
AC4 | Same request becomes Submitted with confirmation/reference and reviewer access. | Lowest-ID coordinator selection, no-candidate refusal, authorised review and response snapshot passed Unit tests. Visible confirmation/reference passed frontend. | Actual persistence, assignment/status atomicity and real stale-state Integration remain unverified. | TC-28-09/10; TC-28-15/16 shared with failure/stale state. | No | P1/P2/P4 implemented with existing columns and APIs. Shared reviewer/manual reassignment permissions unchanged. | Partially Covered
AC5 | Repeat same request without duplicates; identical separate requests remain valid. | Known-ID submitted/Draft/unavailable reconciliation variants passed; Unit submission adds no row/reservation. Backend 409 unchanged. | Real repeat-submit counts/identical separate requests extension and concurrency guarantees pending Integration. | TC-28-14/16; extend TC-28-11. | No | P3/P6 implemented. Initial creation lost-ID idempotency remains deferred to SCRUM-29; no keys/schema changes. | Partially Covered
AC6 | Explain failure and retain information for retry. | No-candidate refusal/retry, simulated post-commit read loss, unknown commit acknowledgement, frontend retention/retry and status checks passed. | Real failed-commit rollback extension unexecuted. Mocked commit/read faults do not establish DB durability. | TC-28-13/14/15; extend TC-28-12. | No | P3/P4/P5 implemented. Unknown status keeps input and performs status checks without resubmitting. | Partially Covered
Minimum production changes
Change / Classification | Affected File / Function | Problem / Impact | Acceptance Criteria | Minimal Proposed Correction | Existing Behaviour Impact | Approval Required? | Test Links / Evidence
P1 Implemented | frontend/src/pages/DraftEventPage.jsx handleSubmit / receipt | No visible unique reference. | AC4 | Existing confirmation displays Request #<Event.id>; no schema/reference mechanism. | Additive UI; no API/model changes. | GREEN authorised and implemented. Broader VERIFY not started. | TC-28-02 existing success extended.
P2 Implemented | backend/app/events/routes.py submit_draft / selector | New unassigned submissions inaccessible to reviewers. | AC4, AC6 | User.query filtered by current coordinator role and ordered by ID. No candidate -> retryable 503 before mutation; assignment/submission share commit. | Cross-story SCRUM-33 integration. Keep manual initial assignment refused; reviewer remains current coordinator. | GREEN authorised and implemented. Broader VERIFY not started. | TC-28-09/10/12. Existing columns suffice.
P3 Implemented | frontend/src/pages/DraftEventPage.jsx handleSubmit / local retry state | Lost successful POST response leaves Draft UI; retry PUT gets 409. | AC5, AC6, AC4 | Draft GET establishes owner-scoped Draft. On 409, mine list establishes non-draft receipt. Keep form values; unknown outcome exposes check-only action. | Backend 409 unchanged; all non-draft outcomes block edits. No new endpoint. | GREEN authorised and implemented. Broader VERIFY not started. | TC-28-14. No matching by content.
P4 Implemented | backend/app/events/routes.py create_draft / save_draft / submit_draft | Post-commit payload refresh can falsely report durable save failure. | AC6; supports AC4 | Focused shared draft payload helper snapshots before commit; creation flushes for ID; invalidated commit connection returns outcome_uncertain. | Same response shape and genuine rollback behaviour. Small shared-route correction. | GREEN authorised and implemented. Broader VERIFY not started. | TC-28-15; TC-28-12/17 regressions. SCRUM-60 pattern.
P5 Implemented | frontend/src/pages/DraftEventPage.jsx input common props / busy | In-flight edits can be overwritten by show(saved). | AC3, AC6 | Relevant form inputs disabled while busy; re-enabled on failure. Submitted/non-draft requests stay read-only. | Temporarily blocks typing during request; values/relaxed drafts unchanged. | GREEN authorised and implemented. Broader VERIFY not started. | TC-28-02 extended pending-request assertions.
P6 Implemented | backend/app/events/routes.py _own_draft / save_draft / submit_draft | Stale/nonserialized Draft check may permit post-submission write. | AC4, AC5; supports AC3 | Fresh Event read with row lock/identity-map refresh before draft save/submit. Review/manual reassignment untouched. | Preserves 409 contract; competing calls may wait. No schema/permission expansion. | GREEN authorised and implemented. Broader VERIFY not started. | TC-28-16 preserved; Integration still blocked. Static implementation review is not concurrency proof.
D1 Assignment resolved | Lowest-ID current coordinator and retryable no-candidate policy implemented. Unit tests passed; no production-role override or advanced assignment.
D2 Idempotency resolved | Known-ID reconciliation implemented; repeat POST still 409. Lost initial creation response without an ID remains deferred to SCRUM-29. No new tables/columns/migrations.
RED history | Approved RED tests retained. Earlier expected failures are recorded in rows 35-42. No assertions weakened. Latest isolated GREEN results are recorded below.
GREEN completed | Only backend/app/events/routes.py and frontend/src/pages/DraftEventPage.jsx changed in production. P1-P6 implemented. Three isolated backend tests and 15 targeted frontend cases passed. Two approved definitions received additive fault/retention assertions and focused rechecks.
VERIFY separately authorised | VERIFY remains separately authorised. First run the preserved stale-state Integration plus five changed backend methods using restricted TEST_DATABASE_URL once connectivity is available. Then select affected auth/draft/review/reassignment regressions; do not infer full coverage from mocks.
GREEN commands | Exact commands/counts are in rows 45-49 and Test Case Plan column Q. No full backend/unit/frontend suite and no DB test was run in GREEN.
Deferred / excluded | Creation-idempotency keys, new request/reference tables, advanced assignment, booking/reservation behaviour, new validation policies, new pages/endpoints, generic retry framework, schema migrations and broad regressions remain excluded/deferred.
Evidence and preservation | Original assertions retained. Existing backend fixtures require no changes: seed users already include coordinators. Two existing SCRUM-28 definitions were strengthened for uncertain commit acknowledgement and newer unsaved edits. Real-DB queries/atomicity/locks remain unverified.
Execution / Environment | Command (exact) | Passed | Failed | Errored | Skipped | Result / Classification | Database Access
Backend isolated Unit (run twice) | .\.venv\Scripts\python.exe -B -m unittest -v tests.test_event_submission.SubmissionUnitTests | 0 | 3 | 0 | 0 | Expected RED, same three assertions both runs. Latest duration 0.031s. | No; Engine/socket guards.
Frontend initial launch | npm test -- src/pages/DraftEventPage.test.jsx --reporter=verbose --reporter=json --outputFile=C:/Users/Mikhail/AppData/Local/Temp/scrum28-frontend-red.json | 0 | 0 | 0 | 0 | npm.ps1 execution-policy error before collection; use npm.cmd, no policy changes. | No.
Frontend sandbox launch | npm.cmd test -- src/pages/DraftEventPage.test.jsx --reporter=verbose --reporter=json --outputFile=C:/Users/Mikhail/AppData/Local/Temp/scrum28-frontend-red.json | 0 | 0 | 0 | 0 | esbuild configuration access denied before collection; authorised rerun outside sandbox. | No; HTTP mocked.
Frontend targeted page | npm.cmd test -- src/pages/DraftEventPage.test.jsx --reporter=verbose --reporter=json --outputFile=C:/Users/Mikhail/AppData/Local/Temp/scrum28-frontend-red.json | 11 | 4 | 0 | 0 | Initial collected run: success extension also had ambiguous status-role query; corrected as test setup, not production RED. | No; HTTP mocked.
Integration attempt | $env:PGCONNECT_TIMEOUT = '5'; .\.venv\Scripts\python.exe -B -m unittest -v tests.test_event_submission.SubmissionPersistenceTests.test_stale_draft_cannot_overwrite_submitted_request | 0 | 0 | 1 | 0 | Setup blocked by sandbox TCP permission. No fixture/assertion ran; no repeat. NOT RED evidence. | Attempted restricted TEST_DATABASE_URL; connection denied.
Frontend corrected rerun (twice) | npm.cmd test -- src/pages/DraftEventPage.test.jsx --testNamePattern 'saves the current edits¦reconciles uncertain submission' --reporter=json --outputFile=C:/Users/Mikhail/AppData/Local/Temp/scrum28-frontend-red-corrected.json | 0 | 4 | 0 | 11 | All four failures now expected production gaps. Eleven cases excluded by name filter; their earlier successful results remain recorded. | No; HTTP mocked.
Distinct latest case results | 3 Unit + 15 frontend cases + 1 Integration attempt | 11 | 7 | 1 | 0 | Count each case once, not rerun attempts. Five existing backend extensions and backend reuse tests remain unexecuted. | No successful DB connection.
GREEN Execution / Scope | Command (exact) | Passed | Failed | Errored | Skipped | Result / Limitations | Database Access
SCRUM-28 isolated backend | .\.venv\Scripts\python.exe -B -m unittest -v tests.test_event_submission.SubmissionUnitTests | 3 | 0 | 0 | 0 | Lowest current coordinator, no-candidate refusal/retry, authorised reviewer scope and post-commit response safety passed. | No; Engine/socket guarded.
Targeted draft page | npm.cmd test -- src/pages/DraftEventPage.test.jsx --reporter=json --outputFile=C:/Users/Mikhail/AppData/Local/Temp/scrum28-frontend-green.json | 15 | 0 | 0 | 0 | All existing/extended/new cases on this page passed. Entire frontend suite not run. | No; HTTP mocked.
Focused post-commit recheck | .\.venv\Scripts\python.exe -B -m unittest -v tests.test_event_submission.SubmissionUnitTests.test_successful_submission_survives_post_commit_read_outage | 1 | 0 | 0 | 0 | Existing definition extended with unknown COMMIT acknowledgement fault. Original assertions retained. | No; simulated commit/read.
Focused reconciliation recheck | npm.cmd test -- src/pages/DraftEventPage.test.jsx --testNamePattern 'reconciles uncertain submission' --reporter=json --outputFile=C:/Users/Mikhail/AppData/Local/Temp/scrum28-reconciliation-green.json | 3 | 0 | 0 | 12 | Three variants passed after newer-edit retention assertion. Twelve unrelated cases on the same page excluded by filter. | No; HTTP mocked.
Distinct latest results | 3 backend Unit + 15 frontend cases | 18 | 0 | 0 | 0 | No remaining isolated failures. Stale-state Integration still blocked; five backend extensions not run. Real transaction/persistence/concurrency verification pending. | No successful DB connection; no GREEN DB attempt.